## Sheet1
BATCH -F REPORT SHEET - MovieTicketBookingApp
NAME | MODULE | DAY 1(March 22) | DAY 2(March 23) | DAY 3(March 24) | DAY4 (March 25) | DAY 5(March 26) | DAY 6(March 30) | DAY 7(March 31)
V SURYA PRAKASH REDDY | Movie Management Module | Pojo Classes Creation, Implementing Service layer | creation of Show Module,Service Layer Impl | Controller for Movie,show | Exceptions for Movie and Show | Testing Movie and Show | Mapping of All Modules | Writing Queries and Final Check
VANKADARI THEJESH | Screen Management Module | Pojo Classes Creation, Implementing Service layer | controller for Screen | Exceptions for Screen | Writing Validators for login and customer | Implementing validators with login | Testing Screen Module | Implementing Log4j
VIDYA SRI MATTA | Login Module | Pojo Classes Creation, Implementing Service layer | created Admin and User module (Partial) | created Admin and User module | Mapping User And Admin modules | Exceptions for login | Admin and Customer accessible modules | Testing and Final Check
YOGENDRA ANNABATTINA | Ticket Management Module | Pojo Classes Creation, Implementing Service layer | Implementing Service layer | Controller for Ticket module | Exceptions for Ticket module | Testing Ticket Module | Helped for Seat Exceptions | Final Check
B. GANGABHAVANI | Customer Module | Pojo Classes Creation, Implementing Service layer | Implementing Service layer | Controller for Customer module | Exceptions for Customer module | Testing Customer Module | Helped for Login Module | Final Check
TELIKAPALLI SRINIVASA USHA SRI | Theatre Management Module | Pojo Classes Creation, Implementing Service layer | controller for Theatre | controller for Theatre | Exceptions for Theatre | Testing Theatre Module | Helped for login module | Final Check
JYOTIKINKAR SAHARIA | Ticket Booking Module | Pojo Classes Creation, Implementing Service layer | controller for Booking | Exceptions for Booking | Creating Seat Module (Pojo and service layer) | Controller for Seat | Exceptions for Seat | Testing Seat module, Final Check